## ProjectTeam
Name | GitHub Alias | Role
Kofi | adams3-sys | Developer
Adrian | zempA570 | Scrum Master
Emily | Etorre1 | Developer
Jasmitha | devaj1 | Developer
Mootaas | abubm1 | Developer
Sinnappah | sinnt1 | Developer
Gausegan | uthag1 | Developer

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual
1 | Calendar - Assign appointment | The user is able to assign himself or another user as responsible for an appointment. Only that user recieves the reminder. | High | 10
2 | Calendar - Click on day | When clicking on a specific day it is "opened" and the appointments appear in detail | Medium | 3
3 | Calendar - Create Delete | The user creates a new appointment. This appointment will be visible in the calendar. The user can delete appointments in the calendar | High | 10
4 | Calendar - Functionality GUI | A Calendar appears with all created appointments | High | 5
5 | Calendar - Reminder function | The user is reminded a certain time in advance of an appointment by a message that pops up when the app is open | Medium | 5
6 | Dashboard - Click on icon | The user wants to select one of the various functions which are accessible from the Dashboard. Thus he expects to be redirected to a "new window" where he is within the selected Function | High | 3 |  | 3
7 | Dashboard - GUI | A window appears that is the "main menu". All functionalities are selectable in icons. | High | 5 |  | 4
8 | Dashboard - Log out | The user is logged out of the webapp when clicking on the "end app/log out" button. | High | 3
9 | Dashboard - Open UserMNGMT | In the dashboard there is a button that opens the user management in a new window. | High | 3 |  | 2
10 | Diary - Create Delete | The user can create new entries himself as well as delete older entries. When creating a new Entry, there should be a Calendar pop-up where he can select date and time of the new entry. | High | 10 | 11 | 12
11 | Diary - Functionality GUI | The user opens the Diary Functionality and can see previously made entries. | High | 5 | 6 | 6
12 | Diary - Mark as important | The user should also be able to mark certain entries as important, so they appear within the "important notes" | Low | 3
13 | General - Back button | When the user is inside a functionality there is "back button" or "home button" in the top left corner. When clicked the dashboard view is opened. (Functionality can be closed and the dashboard opened) | Medium | 3 | 3 | 3
14 | General - Database | A database must be set up and accessed from the code to save user submitted data. | High | 5
15 | Important Notes - Create Edit Delete | The user can add, edit and delete important notes, for example if the patient refuses to take the medicines. All notes are shared between all users. | High | 10 |  | 16
16 | Important Notes - Functionality GUI | All entries are shown in a list that is sorted from oldest to newest (at the bottom). If notes are too long they are shortened and the user must click on them to expand. | High | 5 |  | 9
17 | Important Notes - Warning window | If the user wants to delete an entry, a warning window appears asking the user if he really wants to delete the entry. The user can then click on "delete" to actually delete the entry or on "cancel" to get to the view of all important notes. | Medium | 3
18 | Infobox - Add Delete | The user can add and delete entries in the infobox | High | 10
19 | Infobox - Functionality GUI | All entries are shown in an alphabetical list. The user can click on an entry to expand it and show details. | High | 5
20 | Login - Create account | The user accesses our app, clicks the button "register", it opens a new window, the user enters a password, then the account is created and the user is logged in. The account is assigned a number upon registration. | High | 5
21 | Login - Functionality GUI | The first window that the user sees when the app is opened. | High | 5 |  | 2
22 | Login - Login with existing account | The user logs in with an existing account, if successful it opens the dashboard, if unsuccessful an error message is shown | High | 5
23 | Status - Add Delete | The user can add and delete entries in the statusbox | High | 10 |  | 12
24 | Status - Functionality GUI | The user sees all entries gouped into the three defined categories. | High | 5 |  | 6
25 | Status - Move item | The user can move items from one status to another by drag-and-drop | Low | 10 |  | 5
26 | To-Do-List - Assign item to User | Items in the To-Do-List can be assigned to one of the users. That user will receive an alert the next time he logs into the app. | Medium | 5
27 | To-Do-List - Create Delete | The user enters a free text. The user can afterwards select a category (special, daily, weekly, monthly, yearly). When the user clicks on the button, the entry is added to the other entries. The user can also delete them. | High | 10 |  | 11
28 | To-Do-List - Functionality GUI | A window is opened where all entries are are sorted into the respective categories. Items that are not done are shown before items that are done. | High | 5 |  | 3
29 | To-Do-List - Mark Item as done | Items in the To-Do-List can be marked as "done". This could be done using a checkmark/checkbox. | High | 3
30 | To-Do-List - Recurring items | Items in the To-Do-List can have a certain time period where the have to be done again. For example, if the bank has to be called every month, 3 weeks after completing the task the item should "undo" itself so the user knows it has to be done again. | High | 5
31 | UserMNGMT - Functionality GUI | The user can add and delete Users in this window. | Medium | 5
32 | UserMNGMT - Add a new User | The logged in user wants to add another user to the existing account, so that the account can be shared by multiple users. This does not mean creating a new account, but simply adding a user to the realm of authorized users | High | 3
33 | UserMNGMT - Delete User | The logged in user wants want to delete users. | High | 3
34 | User Regisration | Person register | High | 3
35 | Project Setup | Clean up the project and create example files | High | 5
36 | Project Setup #2 | See if different packaging method works better | Medium | 2
50 | Login/Registering | Everything to do with loggin in and registering | Medium | 10
|  |  | Total | 193
Not implemented
Partially implemented but not functional in final product
Implemented

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
4 | 1 | Calendar - Functionality GUI | The complete GUI for the calendar functionality without any logic. | UI | Thevian |  | Low | 5 |  | 4 | Done
6 | 1 | Dashboard functionality icon - Click | When clicking on an icon a new window with the title of the functionality is opened | Main Window | Kofi |  | High | 3 |  | 2 | In progress
7.1 | 1 | GUI - Dashboard | Create Dashboard GUI, all buttons and icons | Main Window | Kofi |  | High | 5 |  | 4 | Done / Ready for review
11 | 1 | Diary - Functionality GUI | The complete GUI for the diary functionality without any logic. | UI | Mootaas |  | Low | 5 |  | 3 | Done / Ready for review
13 | 1 | Back button - Click | Opens the previous view. Usually opens the dashboard when viewing a functionality. | UI, Controller | Mootaas |  | High | 3 |  | 1 | Done / Ready for review
14.2 | 1 | Database setup & connection | Setup the database and acces it from code (add, edit, get, delete) | Database | Adrian |  | High | 2 |  | 4 | In progress
16 | 1 | Important Notes - Functionality GUI | The complete GUI for the important notes functionality without any logic. | UI | Thevian |  | Medium | 5 |  |  | Thevian take over
18.1 | 1 | Infobox - add function | Function to add new entry to the infobox | UI, Controller | Gausi |  | Medium | 2 |  | 4 | Ready for merge
18.2 | 1 | Infobox - delete function | Function to delete existing entry from infobox | UI, Controller | Gausi |  | Medium | 2 |  | 4 | Ready for merge
18.3 | 1 | Infobox - edit function | Function to edit existing entry in the infobox | UI, Controller | Gausi |  | Medium | 2 |  | 4 | Ready for merge
18.4 | 1 | Infobox - get stuff function | Function to get entries from database | UI, Controller | Gausi |  | Medium | 2 |  | 4 | Ready for merge
18.5 | 1 | Infobox - show function | Function to show all entries in GUI | UI, Controller | Gausi |  | Medium | 2 |  | 4 | Ready for merge
19 | 1 | Infobox - Functionality GUI | The complete GUI for the infobox functionality without any logic. | UI | Gausi |  | High | 5 |  |  | Ready for merge
21 | 1 | Login - Functionality GUI | The complete GUI for the login screen without any logic. | UI | Jasy |  | Low | 5 |  | 1 | In progress
24 | 1 | Status - Functionality GUI | The complete GUI for the status functionality without any logic. | UI | Emily |  | Low | 5 |  | 4 | Done / Ready for Pull request
28 | 1 | To-Do-List - Functionality GUI | The complete GUI for the to-do-list functionality without any logic. | UI | Jasy |  | Low | 5 |  | 3 | In progress
31 | 1 | UserMNGMT - GUI | The complete GUI for the user management without any logic. | UI | Adrian |  | Low | 5 |  | 3 | In progress
34 | 1 | Register - Functionality GUI | Person Register | UI | Gausi |  | High | 5
35 | 1 | Project setup | Clean up the project and create example files | Setup | Adrian |  | High | 5 |  | 5 | Done
|  |  |  | Sprint 1 W1+2 |  |  | Total | 73 | 0 | 54
6 | 2 | Dashboard functionality icon - Click | When clicking on an icon a new window with the title of the functionality is opened | Main Window | Kofi |  | High | 3 |  | 4 | Ready for merge
14.2 | 2 | Database setup & connection | Setup the database and acces it from code (add, edit, get, delete) | Database | Adrian |  | High | 2 |  | 5 | Done
16 | 2 | Important Notes - Functionality GUI | The complete GUI for the important notes functionality without any logic. | UI | Thevian |  | Medium | 5 |  | 3 | Ready for merge
18.1 | 2 | Infobox - add function | Function to add new entry to the infobox | UI, Controller | Gausi |  | Medium | 2 |  | 8 | In progress
18.2 | 2 | Infobox - delete function | Function to delete existing entry from infobox | UI, Controller | Gausi |  | Medium | 2 |  | 8 | In progress
18.4 | 2 | Infobox - get stuff function | Function to get entries from database | UI, Controller | Gausi |  | Medium | 2 |  | 8 | In progress
18.5 | 2 | Infobox - show function | Function to show all entries in GUI | UI, Controller | Gausi |  | Medium | 2 |  | 8 | In progress
19 | 2 | Infobox - Functionality GUI | The complete GUI for the infobox functionality without any logic. | UI | Gausi |  | High | 5 |  | 8 | ready for Merge
21 | 2 | Login - Functionality GUI | The complete GUI for the login screen without any logic. | UI | Adrian |  | Low | 5 |  | 1 | In progress
28 | 2 | To-Do-List - Functionality GUI | The complete GUI for the to-do-list functionality without any logic. | UI | Jasy |  | Low | 5 |  | 2 | In progress
31 | 2 | UserMNGMT - GUI | The complete GUI for the user management without any logic. | UI | Adrian |  | Low | 5 |  | 4 | Done
34 | 2 | Register - Functionality GUI | Person Register | UI | Gausi |  | High | 5 |  | 1 | In progress
3 | 2 | Calendar (Create and Delete) | The user creates a new appointment. This appointment will be visible in the calendar. The user can edit and delete appointments in the calendar | UI | Thevian |  | High | 10 |  |  | Gui is finished, in progress (Database)
10 | 2 | Diary (Create, Edit, Delete) | The user can create new entries himself as well as edit or delete older entries. When creating a new Entry, there should be a Calendar pop-up where he can select date and time of the new entry. | UI | Mootaas |  | High | 10 |  |  | Done
20 | 2 | Login (create Account) | The user accesses our app, clicks the button "register", it opens a new window, the user enters a password, then the account is created and the user is logged in. The account is assigned a number upon registration. | UI, Database | Adrian |  | High | 5 |  |  | In progress
23 | 2 | Status (Add,Edit, Delete) | The user can add, edit and delete entries in the statusbox | UI, Database | Emily |  | High | 10 |  | 4 | add - done, delete - in progress
27 | 2 | § | The user enters a free text. The user can afterwards select a category (special, daily, weekly, monthly, yearly). When the user clicks on the button, the entry is added to the other entries. The user can also edit entries and delete them. | UI, Database | Jasy / Thevian |  | High | 10 |  |  | Gui is finished, in progress (Database)
33 | 2 | UserMNGMT - Delete /Edit User | The logged in user wants want to edit or delete users. The users are | UI, Database | Adrian |  | High | 3 |  | 3 | Done
32 | 2 | UserMNGMT - Add a new User | The logged in user wants to add another user to the existing account, so that the account can be shared by multiple users. This does not mean creating a new account, but simply adding a user to the realm of authorized users | UI, Database | Adrian |  | High | 3 |  | 3 | Done
36 | 2 | Project Setup #2 | See if different packaging method works better | Project Setup | Adrian |  | Medium | 3 |  | 2 | In progress
|  |  |  | Sprint 2 W1+2 |  |  | Total | 97 | 0 | 64
18 | 3 | Infobox - Add Delete | The user can add and delete entries in the infobox |  | Gausi |  | High | 10 |  | 20 | Done
3 | 3 | Calendar (Create and Delete) | The user creates a new appointment. This appointment will be visible in the calendar. The user can edit and delete appointments in the calendar | UI | Thevian |  | High | 10 |  | 8 | Done
10 | 3 | Diary (Create, Delete) | The user can create new entries himself as well as edit or delete older entries. When creating a new Entry, there should be a Calendar pop-up where he can select date and time of the new entry. | UI | Mootaas |  | High | 10 |  | 8 | Done
23 | 3 | Status (Add, Delete) | The user can add, edit and delete entries in the statusbox | UI, Database | Emily |  | High | 10 |  | 15 | Done
27 | 3 | To Do List (Create, Delete) | The user enters a free text. The user can afterwards select a category (special, daily, weekly, monthly, yearly). When the user clicks on the button, the entry is added to the other entries. The user can also edit entries and delete them. | UI, Database | Jasy |  | High | 10 |  | 9 | Done
36 | 3 | Project Setup #2 | See if different packaging method works better | Project Setup | Adrian |  | Medium | 3 |  | 5 | Done
50.1 | 3 | Login / Register GUI | Check and update both GUIs | UI | Adrian |  | Low | 1 |  | 3 | Deprecated
50.2 | 3 | Model for Patient / User | Create Model for Patient and update Model for User/rRelatives | [6 empty] | 1 | Deprecated
20 | 3 | Login (create Account) | The user accesses our app, clicks the button "register", it opens a new window, the user enters a password, then the account is created and the user is logged in. The account is assigned a number upon registration. | UI, Database | Adrian |  | High | 5 |  | 4 | Deprecated
22 | 3 | Login - Login with existing account | The user logs in with an existing account, if successful it opens the dashboard, if unsuccessful an error message is shown |  | Adrian |  | High | 5 |  | 5 | Deprecated
34 | 3 | User Regisration | Person register |  | Adrian |  | High | 3 |  | 2 | Deprecated
37 | 3 | Transform into MVP pattern |  |  | Adrian |  | Very High | 10 |  | 20 | Done
|  |  |  | Sprint 2 W3 |  |  | Total | 67 | 0 | 80
(To Do)
In progress
Ready for review
In review
Ready for merge
Done
4 | 1 | Calendar - Functionality GUI | The complete GUI for the calendar functionality without any logic. | UI | Emily | Adrian | Low | 5 | 3 |  | Done - Missing calendar view
6 | 1 | Dashboard functionality icon - Click | When clicking on an icon a new window with the title of the functionality is opened | Main Window | Kofi |  | High | 3 |  |  | WIP
7.1 | 1 | GUI - Dashboard | Create Dashboard GUI, all buttons and icons | Main Window | Kofi | Thevi | High | 5 |  | 2 | Done - still room for adaptions
7.2 | 1 | GUI - Every functionality | Create a placeholder GUI for all functions with the title of the functionality and "back button" | UI |  |  | Low | 1
11 | 1 | Diary - Functionality GUI | The complete GUI for the diary functionality without any logic. | UI | Emily |  | Low | 5 | 2 |  | In progress - Can't import Icons
13 | 1 | Back button - Click | Opens the previous view. Usually opens the dashboard when viewing an functionality. | UI, Controller | Mootaas |  | High | 3 |  |  | In progress
14.1 | 1 | Database information | Gather information about connecting database to project | Database | Adrian | - | High | 3 |  | 1.5 | Done
14.2 | 1 | Database setup & connection | Setup the database and acces it from code (add, edit, get, delete) | Database | Adrian |  | High | 2
16 | 1 | Important Notes - Functionality GUI | The complete GUI for the important notes functionality without any logic. | UI | Jasy |  | Medium | 5 |  | 1.5 | Done - spacing between the components needed
18.1 | 1 | Infobox - add function | Function to add new entry to the infobox | UI, Controller | Gausi |  | Medium | 2 |  | 2 | merge done
18.2 | 1 | Infobox - delete function | Function to delete existing entry from infobox | UI, Controller | Gausi |  | Medium | 2 |  | 2 | merge done
18.3 | 1 | Infobox - edit function | Function to edit existing entry in the infobox | UI, Controller | Gausi |  | Medium | 2 |  | 2 | merge done
18.4 | 1 | Infobox - get stuff function | Function to get entries from database | UI, Controller | Gausi |  | Medium | 2
18.5 | 1 | Infobox - show function | Function to show all entries in GUI | UI, Controller | Gausi |  | Medium | 2 |  | 2 | merge done
19 | 1 | Infobox - Functionality GUI | The complete GUI for the infobox functionality without any logic. | UI | Emily |  | High | 5 |  | 1.5 | Done - but it was deleted after eclipse update
21 | 1 | Login - Functionality GUI | The complete GUI for the login screen without any logic. | UI | Jasy |  | Low | 5 |  | 2
24 | 1 | Status - Functionality GUI | The complete GUI for the status functionality without any logic. | UI | Emily |  | Low | 5 |  | 1 | Failed because of Eclipse old version
28 | 1 | To-Do-List - Functionality GUI | The complete GUI for the to-do-list functionality without any logic. | UI | Jasy |  | Low | 5 |  | 2 | Done - spacing between the components needed
31 | 1 | UserMNGMT - GUI | The complete GUI for the user management without any logic. | UI |  |  | Low | 5
34 | 1 | Register - Functionality GUI | Person Register | UI | Gausi |  | High | 5 |  | 2 | merge done
|  |  | Created Manual on how to setup project with GIT and use it. |  | Adrian |  |  |  |  | 8
|  |  | Setup GIT so we can interact in the group on the same repository |  | Everyone |  |  |  |  | 10
[7 empty] | Total | 72 | 5 | 39.5
(To Do)
In progress
Done
In review
Ready for merge
1.1 | 2 | Patient Model | Data model for patient record needs to be created based on standard.... | Database |  |  | medium | 2
1.2 | 2 |  |  | UI, Controller |  |  | high | 8
1.3 | 1 |  |  | All |  |  | high | 16
2.1 | 1 |  |  | Database |  |  | low | 4
2.2 | 2 |  |  | Main Window |  |  | high | 8
DO NOT TOUCH - MIGHT NEED LATER
2.1 |  |  | Design Dashboard
Create "Back to Main Button" for each Function
3.1 |  |  | Implement and Create a Calendar
Design Calendar and Entry Window
Allowing Entries to be made, combined with a specific date out of the calendar
Optional: Tag user(s) for an entry so they get an entry into their calendar as well
Delete or edit an existing Appointment/Entry
Functionality that when clicking on a day, the entries of this day are shown in detail
4.1 |  |  | Design Diary Function with Possibilties to Add, Edit and Delete Entries
MArk Entries as Important so they can be duplicated within "Important Notes"
implement and create "statusbox"
define categories "Selbstständig" / "Teilweise Selbstständig" / "mit Hilfe"
23 |  | status add | Entry a status and choose the category, date of the entry and Username
23.1 |  | status edit | status can be edited by everyone?, update the dates, so could be sure about the last day when it was possible / not possible to do it for the patient
23.2 |  | status delete | delete the status, only if the same user has created it
23.3 |  | status move | Status can be moved by other user by changing the category
When the user clicks the plus button, a window opens with a calendar view and a text field. The user chooses the date first. Then the user can write in the text field. If he clicks the Add button below the text field, the entry is added.
The user clicks on a specific entry. Then the user clicks on the edit button. Now the user can edit the entry, or delete it.

## BurndownChart
Sprint | Day of record | Sprint day | Remaining Effort | Remaining Ressources | Completed Tasks
1 | 21.11.2019 | 1 | 72 | 72 | 0
1 | 22.11.2019 | 2 | 60 | 62 | 1
1 | 23.11.2019 | 3 | 45 | 52 | 0
1 | 24.11.2019 | 4 | 40 | 42 | 3
1 | 25.11.2019 | 5 | 35 | 32 | 2
1 | 26.11.2019 | 6 | 40 | 22 | 0
1 | 27.11.2019 | 7 | 20 | 11 | 0
1 | 28.11.2019 | 8 | 5 | 1 | 1
1 | 29.11.2019 | 9 | 4 | 0 | 2

## Notizen
Info:
06. Dezember: Rücksprache mit Marcel Pfahrer, Add-Ons sind erlaubt und für den Kalender OK, Implementation im Code ist nicht wichtig ob Deutsch oder Englisch